## Summary
BRYT Report Builder POC - Estimate Summary
Phase | Tasks | Required (days) | Optional (days) | Total (days)
Phase 1: Foundations | 3 | 0.75 | 0 | 0.75
Phase 2: Query generation + validation | 3 | 0.75 | 0 | 0.75
Phase 3: Backend services | 4 | 1.25 | 0 | 1.25
Phase 4: Run + preview + download | 3 | 0 | 0 | 0
Phase 5: Frontend | 3 | 3.5 | 0 | 3.5
Phase 6: Demo readiness | 2 | 0.5 | 0 | 0.5
TOTAL | 18 | 6.75 | 0 | 6.75

## Task Detail
Estimate | Task ID | Task Description | Category | Days | Optional
Phase 1: Foundations | 1 | Scaffold the POC project | scaffold | 0.5
Phase 1: Foundations | 2 | Define `core` domain types | core | 0.125
Phase 1: Foundations | 3 | Bring in the Join_Manifest + demo allow-list | core | 0.125
Phase 2: Query generation + validation | 4 | Implement `validateDesign(design, catalog, manifest) | core | 0.25
Phase 2: Query generation + validation | 5 | Implement `Query_Generator` (design + catalog + manifest → SQL) | core | 0.25
Phase 2: Query generation + validation | 6 | Implement `Report_Design` serialise/deserialise round-trip | core | 0.25
Phase 3: Backend services | 7 | Catalog service (static / cached) | backend | 0.25
Phase 3: Backend services | 8 | Reports CRUD (simple store) | backend | 0.25
Phase 3: Backend services | 9 | Assistant chat handler — Converse tool-use loop (the star) | assistant | 0.5
Phase 3: Backend services | 10 | Optional `validate_query` dry-run (`EXPLAIN`) polish | assistant | 0.25
Phase 4: Run + preview + download | 11 | Run handler (generate → Athena → CSV, no Step Functions) | run | 0
Phase 4: Run + preview + download | 12 | CSV download handler | run | 0
Phase 4: Run + preview + download | 13 | Preview handler | run | 0
Phase 5: Frontend | 14 | Flow-canvas library spike | frontend | 1
Phase 5: Frontend | 15 | Client `Report_Design` model + graph mapping | frontend | 0.5
Phase 5: Frontend | 16 | Screens | frontend | 2
Phase 6: Demo readiness | 17 | Seed a demo report + demo data | demo | 0.25
Phase 6: Demo readiness | 18 | End-to-end demo run-through | demo | 0.25