## Summary
BRYT Contract Note Rework - Estimate Summary
Estimate | Sub-Tasks | Required (days) | Optional (days) | Total (days)
Est 1: PDF/Template Management | 43 | 20.25 | 4.5 | 24.75
Est 2: DocuSign Integration | 25 | 10.5 | 3 | 13.5
Est 3a: Training & Enablement | 7 | 8 | 0 | 8
Est 3b: Data Source Extensibility | 26 | 12.75 | 2.5 | 15.25
Est 4: Bespoke Contracts | 25 | 11.25 | 3 | 14.25
Est 5: Comparison Audit | 16 | 16.5 | 0 | 16.5
TOTAL | 142 | 79.25 | 13 | 92.25

## Task Detail
Estimate | Task ID | Task Description | Category | Days | Optional
Est 1: PDF/Template Management | 1.1 | Define CDK infrastructure for DynamoDB table, S3 buckets, and API Gateway routes | infrastructure | 1
Est 1: PDF/Template Management | 1.2 | Create shared TypeScript interfaces and types | api_backend | 0.5
Est 1: PDF/Template Management | 1.3 | Implement specification tree validation utility | api_backend | 0.5
Est 1: PDF/Template Management | 1.4 | Write property tests for specification tree validation | testing | 0.5 | Yes
Est 1: PDF/Template Management | 2.1 | Implement `list-templates` handler | api_backend | 0.5
Est 1: PDF/Template Management | 2.2 | Implement `create-template` handler | api_backend | 0.5
Est 1: PDF/Template Management | 2.3 | Implement `get-template` handler | api_backend | 0.5
Est 1: PDF/Template Management | 2.4 | Implement `update-template` handler | api_backend | 0.5
Est 1: PDF/Template Management | 2.5 | Implement `delete-template` handler | api_backend | 0.5
Est 1: PDF/Template Management | 2.6 | Implement `reorder-templates` handler | api_backend | 0.5
Est 1: PDF/Template Management | 2.7 | Write property tests for template API logic | testing | 0.5 | Yes
Est 1: PDF/Template Management | 3.1 | Implement `list-sections` handler | api_backend | 0.5
Est 1: PDF/Template Management | 3.2 | Implement `add-section` handler | api_backend | 0.5
Est 1: PDF/Template Management | 3.3 | Implement `remove-section` handler | api_backend | 0.5
Est 1: PDF/Template Management | 3.4 | Implement `reorder-sections` handler | api_backend | 0.5
Est 1: PDF/Template Management | 3.5 | Implement `get-section-schema` and `save-section-schema` handlers | api_backend | 0.5
Est 1: PDF/Template Management | 3.6 | Implement section version history handlers | api_backend | 0.5
Est 1: PDF/Template Management | 3.7 | Implement shared section CRUD handlers | api_backend | 0.5
Est 1: PDF/Template Management | 3.8 | Implement template change log | api_backend | 0.5
Est 1: PDF/Template Management | 3.9 | Write property tests for section API logic | testing | 0.5 | Yes
Est 1: PDF/Template Management | 4.1 | Implement `get-rule` handler | api_backend | 0.5
Est 1: PDF/Template Management | 4.2 | Implement `save-rule` handler | api_backend | 0.5
Est 1: PDF/Template Management | 6.1 | Implement specification evaluator | api_backend | 0.5
Est 1: PDF/Template Management | 6.2 | Write property tests for specification evaluator | testing | 0.5 | Yes
Est 1: PDF/Template Management | 6.3 | Implement template selection logic | api_backend | 0.5
Est 1: PDF/Template Management | 6.4 | Implement section renderer | api_backend | 0.5
Est 1: PDF/Template Management | 6.5 | Write property test for section rendering | testing | 0.5 | Yes
Est 1: PDF/Template Management | 6.6 | Implement PDF stitcher | api_backend | 0.5
Est 1: PDF/Template Management | 6.7 | Write property test for PDF stitching | testing | 0.5 | Yes
Est 1: PDF/Template Management | 6.8 | Implement XML-to-JSON parser and S3 trigger handler | api_backend | 0.5
Est 1: PDF/Template Management | 6.9 | Write property tests for pipeline | testing | 0.5 | Yes
Est 1: PDF/Template Management | 8.1 | Create ContractNoteModule with routing | frontend | 0.75
Est 1: PDF/Template Management | 8.2 | Implement TemplateService, SectionService, and RulesService | frontend | 0.75
Est 1: PDF/Template Management | 9.1 | Implement TemplateListComponent | frontend | 0.75
Est 1: PDF/Template Management | 9.2 | Implement TemplateEditComponent | frontend | 0.75
Est 1: PDF/Template Management | 9.2a | Implement SectionVersionHistoryComponent | frontend | 0.75
Est 1: PDF/Template Management | 9.3 | Implement RulesConfigComponent | frontend | 0.75
Est 1: PDF/Template Management | 9.4 | Implement SectionEditorComponent (Web Component wrapper for pdf-me Designer) | frontend | 0.75
Est 1: PDF/Template Management | 9.5 | Implement SharedSectionsComponent and SharedSectionDetailComponent | frontend | 0.75
Est 1: PDF/Template Management | 9.6 | Write unit tests for Angular components | testing | 0.5 | Yes
Est 1: PDF/Template Management | 11.1 | Wire CDK deployment for all components | infrastructure | 1
Est 1: PDF/Template Management | 11.2 | Add navigation entry in Admin Portal sidebar for Contract Note Templates | integration | 0.75
Est 1: PDF/Template Management | 11.3 | Write integration tests for full pipeline flow | testing | 0.5 | Yes
Est 2: DocuSign Integration | 1.1 | Define CDK infrastructure for DynamoDB table, S3 bucket, API Gateway, and Secrets Manager | infrastructure | 1
Est 2: DocuSign Integration | 1.2 | Create shared TypeScript interfaces and types | api_backend | 0.5
Est 2: DocuSign Integration | 1.3 | Implement retry utility with exponential backoff | api_backend | 0.5
Est 2: DocuSign Integration | 1.4 | Implement error record writer utility | api_backend | 0.5
Est 2: DocuSign Integration | 2.1 | Implement Salesforce OAuth client | api_backend | 0.5
Est 2: DocuSign Integration | 2.2 | Implement customer contact lookup | api_backend | 0.5
Est 2: DocuSign Integration | 2.3 | Implement signed document upload to Salesforce | api_backend | 0.5
Est 2: DocuSign Integration | 2.4 | Write property tests for Salesforce client | testing | 0.5 | Yes
Est 2: DocuSign Integration | 3.1 | Implement DocuSign JWT authentication | api_backend | 0.5
Est 2: DocuSign Integration | 3.2 | Implement envelope creation | api_backend | 0.5
Est 2: DocuSign Integration | 3.3 | Implement signed document download | api_backend | 0.5
Est 2: DocuSign Integration | 3.4 | Implement HMAC webhook signature validation | api_backend | 0.5
Est 2: DocuSign Integration | 3.5 | Write property tests for DocuSign client | testing | 0.5 | Yes
Est 2: DocuSign Integration | 4.1 | Implement DynamoDB metadata operations | api_backend | 0.5
Est 2: DocuSign Integration | 4.2 | Write property tests for metadata service | testing | 0.5 | Yes
Est 2: DocuSign Integration | 5.1 | Implement S3 event handler and contract metadata extraction | api_backend | 0.5
Est 2: DocuSign Integration | 5.2 | Implement send envelope orchestration | api_backend | 0.5
Est 2: DocuSign Integration | 5.3 | Write property tests for send envelope flow | testing | 0.5 | Yes
Est 2: DocuSign Integration | 7.1 | Implement webhook request handler | api_backend | 0.5
Est 2: DocuSign Integration | 7.2 | Implement completion flow | api_backend | 0.5
Est 2: DocuSign Integration | 7.3 | Implement declined/expired flow | api_backend | 0.5
Est 2: DocuSign Integration | 7.4 | Write property tests for webhook handler | testing | 0.5 | Yes
Est 2: DocuSign Integration | 9.1 | Wire CDK deployment for all components | infrastructure | 1
Est 2: DocuSign Integration | 9.2 | Configure contract metadata sidecar in Estimate 1 render pipeline | api_backend | 0.5
Est 2: DocuSign Integration | 9.3 | Write integration tests for full pipeline flow | testing | 0.5 | Yes
Est 3b: Data Source Extensibility | 1.1 | Modify Project Role trust policy to allow Lambda assumption | infrastructure | 1
Est 3b: Data Source Extensibility | 1.2 | Configure Athena workgroup and results bucket | infrastructure | 1
Est 3b: Data Source Extensibility | 1.3 | Add DynamoDB records for template data source attachments | api_backend | 0.5
Est 3b: Data Source Extensibility | 2.1 | Implement Glue catalog client (assumes Project Role) | api_backend | 0.5
Est 3b: Data Source Extensibility | 2.2 | Implement column detail fetcher | api_backend | 0.5
Est 3b: Data Source Extensibility | 2.3 | Write property tests for discovery | testing | 0.5 | Yes
Est 3b: Data Source Extensibility | 3.1 | Implement `list-available` handler | api_backend | 0.5
Est 3b: Data Source Extensibility | 3.2 | Implement `get-columns` handler | api_backend | 0.5
Est 3b: Data Source Extensibility | 3.3 | Implement `attach-data-source` handler | api_backend | 0.5
Est 3b: Data Source Extensibility | 3.4 | Implement `detach-data-source` handler | api_backend | 0.5
Est 3b: Data Source Extensibility | 3.5 | Implement `list-attached` handler | api_backend | 0.5
Est 3b: Data Source Extensibility | 3.6 | Write property tests for data source API | testing | 0.5 | Yes
Est 3b: Data Source Extensibility | 4.1 | Implement Athena query executor | api_backend | 0.5
Est 3b: Data Source Extensibility | 4.2 | Implement enrichment orchestrator | api_backend | 0.5
Est 3b: Data Source Extensibility | 4.3 | Integrate enrichment step into render pipeline | api_backend | 0.5
Est 3b: Data Source Extensibility | 4.4 | Write property tests for enrichment | testing | 0.5 | Yes
Est 3b: Data Source Extensibility | 6.1 | Implement DataSourceService | frontend | 0.75
Est 3b: Data Source Extensibility | 6.2 | Extend TemplateEditComponent with Data Sources panel | frontend | 0.75
Est 3b: Data Source Extensibility | 6.3 | Implement data source picker dialog | api_backend | 0.5
Est 3b: Data Source Extensibility | 7.1 | Extend SectionEditorComponent to show data source fields | frontend | 0.75
Est 3b: Data Source Extensibility | 7.2 | Implement shared section dependency tracking | api_backend | 0.5
Est 3b: Data Source Extensibility | 7.3 | Implement shared section attachment dependency check | api_backend | 0.5
Est 3b: Data Source Extensibility | 7.4 | Display data source dependencies on Shared Section detail screen | api_backend | 0.5
Est 3b: Data Source Extensibility | 7.5 | Write property tests for frontend logic | testing | 0.5 | Yes
Est 3b: Data Source Extensibility | 9.1 | Wire CDK deployment for new components | infrastructure | 1
Est 3b: Data Source Extensibility | 9.2 | Write integration tests | testing | 0.5 | Yes
Est 4: Bespoke Contracts | 1.1 | Implement Salesforce bespoke flag check in render pipeline | api_backend | 0.5
Est 4: Bespoke Contracts | 1.2 | Implement pending bespoke record creation | api_backend | 0.5
Est 4: Bespoke Contracts | 1.3 | Write property tests for pipeline skip | testing | 0.5 | Yes
Est 4: Bespoke Contracts | 2.1 | Implement `list-bespoke` handler | api_backend | 0.5
Est 4: Bespoke Contracts | 2.2 | Implement `create-bespoke` handler | api_backend | 0.5
Est 4: Bespoke Contracts | 2.3 | Implement `get-bespoke` handler | api_backend | 0.5
Est 4: Bespoke Contracts | 2.4 | Implement `update-bespoke` and `delete-bespoke` handlers | api_backend | 0.5
Est 4: Bespoke Contracts | 2.5 | Implement bespoke section management | api_backend | 0.5
Est 4: Bespoke Contracts | 2.6 | Implement `get-contract-data` handler | api_backend | 0.5
Est 4: Bespoke Contracts | 2.7 | Write property tests for bespoke API | testing | 0.5 | Yes
Est 4: Bespoke Contracts | 3.1 | Implement `render-bespoke` handler | api_backend | 0.5
Est 4: Bespoke Contracts | 3.2 | Implement `list-renders` handler | api_backend | 0.5
Est 4: Bespoke Contracts | 3.3 | Write property tests for on-demand render | testing | 0.5 | Yes
Est 4: Bespoke Contracts | 5.1 | Implement `send-docusign` handler | api_backend | 0.5
Est 4: Bespoke Contracts | 5.2 | Write property tests for DocuSign trigger | testing | 0.5 | Yes
Est 4: Bespoke Contracts | 6.1 | Create BespokeModule with routing and BespokeService | frontend | 0.75
Est 4: Bespoke Contracts | 6.2 | Implement BespokeListComponent | frontend | 0.75
Est 4: Bespoke Contracts | 6.3 | Implement BespokeEditComponent | frontend | 0.75
Est 4: Bespoke Contracts | 6.4 | Implement ContractDataReferencePanel | api_backend | 0.5
Est 4: Bespoke Contracts | 6.5 | Implement BespokeRenderHistoryComponent | frontend | 0.75
Est 4: Bespoke Contracts | 6.6 | Implement creation flow (template picker dialog) | api_backend | 0.5
Est 4: Bespoke Contracts | 6.7 | Write unit tests for bespoke components | testing | 0.5 | Yes
Est 4: Bespoke Contracts | 8.1 | Wire CDK deployment | infrastructure | 1
Est 4: Bespoke Contracts | 8.2 | Add navigation entry in Admin Portal sidebar for Bespoke Contract Notes | integration | 0.75
Est 4: Bespoke Contracts | 8.3 | Write integration tests | testing | 0.5 | Yes
Est 5: Comparison Audit | 1.1 | Define CDK infrastructure | infrastructure | 1
Est 5: Comparison Audit | 1.2 | Configure Athena for results querying | infrastructure | 1
Est 5: Comparison Audit | 2.1 | Implement `comparison-fetch-original` Lambda | api_backend | 0.5
Est 5: Comparison Audit | 3.1 | Implement Graph API OAuth client | api_backend | 0.5
Est 5: Comparison Audit | 3.2 | Implement mailbox search | api_backend | 0.5
Est 5: Comparison Audit | 3.3 | Implement attachment extraction | api_backend | 0.5
Est 5: Comparison Audit | 4.1 | Implement `comparison-invoke-bedrock` Lambda | api_backend | 0.5
Est 5: Comparison Audit | 4.2 | Create initial comparison prompt | api_backend | 0.5
Est 5: Comparison Audit | 5.1 | Implement `comparison-init` Lambda | api_backend | 0.5
Est 5: Comparison Audit | 5.2 | Implement `comparison-store-finding` Lambda | api_backend | 0.5
Est 5: Comparison Audit | 5.3 | Implement `comparison-update-summary` Lambda | api_backend | 0.5
Est 5: Comparison Audit | 7.1 | Iteration cycle 1: Run batch, review Bedrock output quality | prompt_iteration | 3
Est 5: Comparison Audit | 7.2 | Iteration cycle 2: Refine based on BRYT feedback | prompt_iteration | 3
Est 5: Comparison Audit | 7.3 | Iteration cycle 3+: Final refinement | prompt_iteration | 3
Est 5: Comparison Audit | 8.1 | Create Athena queries for common analysis patterns | api_backend | 0.5
Est 5: Comparison Audit | 8.2 | Produce first spreadsheet report for BRYT | api_backend | 0.5