## Summary
BRYT Report Builder - Estimate Summary
Phase | Tasks | Required (days) | Optional (days) | Total (days)
Phase 1: Repo & shared-lib foundations | 4 | 1.25 | 0 | 1.25
Phase 2: Security spine | 6 | 2.25 | 2 | 4.25
Phase 3: CDK foundation | 6 | 0.75 | 0 | 0.75
Phase 4: Catalog + Reports CRUD | 3 | 0.75 | 0 | 0.75
Phase 5: Assistant (Converse loop) + query generation | 6 | 4.75 | 2 | 6.75
Phase 6: Run pipeline + preview + download | 6 | 1.25 | 2 | 3.25
Phase 7: Frontend (Angular Customer Portal extension) | 3 | 3 | 2 | 5
Phase 8: Hardening, tests, deploy | 4 | 2.5 | 1 | 3.5
TOTAL | 38 | 16.5 | 9 | 25.5

## Task Detail
Estimate | Task ID | Task Description | Category | Days | Optional
Phase 1: Repo & shared-lib foundations | 1 | Scaffold the `BrytReportBuilder` repo | scaffold | 0.5
Phase 1: Repo & shared-lib foundations | 2 | Define `shared-lib` domain types | api_backend | 0.25
Phase 1: Repo & shared-lib foundations | 3 | Promote the Join_Manifest into `shared-lib | api_backend | 0.25
Phase 1: Repo & shared-lib foundations | 4 | Port shared HTTP + identity helpers | api_backend | 0.25
Phase 2: Security spine | 5 | Implement `validateDesign(design, catalog, manifest) | security_core | 0.5
Phase 2: Security spine | 6 | Implement identity & `Authorised_Bryt_Numbers` resolution (`shared/identity`) | security_core | 0.5
Phase 2: Security spine | 7 | Implement `Query_Generator` (pure: design + catalog + manifest + bounds + trusted context → SQL) | security_core | 0.5
Phase 2: Security spine | 8 | Implement `Query_Verifier` (independent of the model — pre-exec + result-set) | security_core | 0.5
Phase 2: Security spine | 9 | Implement `Report_Design` serialise/deserialise round-trip | api_backend | 0.25
Phase 2: Security spine | 10 | Property tests for the security spine (P1–P5, P7, P8) | testing | 2 | Yes
Phase 3: CDK foundation | 11 | DynamoDB single table | infrastructure | 0.125
Phase 3: CDK foundation | 12 | S3 buckets | infrastructure | 0.125
Phase 3: CDK foundation | 13 | API Gateway REST API + JWT authorizer | infrastructure | 0.125
Phase 3: CDK foundation | 14 | Per-environment execution role (IAM **and** Lake Formation) | infrastructure | 0.125
Phase 3: CDK foundation | 15 | Athena workgroup + config | infrastructure | 0.125
Phase 3: CDK foundation | 16 | Health/smoke route + confirm a dev-stage deploy | integration | 0.125
Phase 4: Catalog + Reports CRUD | 17 | Catalog service (fail-closed) | api_backend | 0.25
Phase 4: Catalog + Reports CRUD | 18 | Reports CRUD (all owner-scoped) | api_backend | 0.25
Phase 4: Catalog + Reports CRUD | 19 | Report-design S3 snapshot on save | api_backend | 0.25
Phase 5: Assistant (Converse loop) + query generation | 20 | Assistant chat handler — Converse tool-use loop | assistant | 1
Phase 5: Assistant (Converse loop) + query generation | 21 | Report_Design mutation tools | assistant | 1
Phase 5: Assistant (Converse loop) + query generation | 22 | validate_query` tool (dry-run) + forced tool choice | assistant | 1
Phase 5: Assistant (Converse loop) + query generation | 23 | Conversation persistence (owner + report scoped) | api_backend | 0.25
Phase 5: Assistant (Converse loop) + query generation | 24 | Prompt-injection defence + audit logging | assistant | 1.5
Phase 5: Assistant (Converse loop) + query generation | 25 | Assistant/injection property + integration tests | testing | 2 | Yes
Phase 6: Run pipeline + preview + download | 26 | Step Functions run pipeline | api_backend | 0.25
Phase 6: Run pipeline + preview + download | 27 | Run queue / status / list APIs | api_backend | 0.25
Phase 6: Run pipeline + preview + download | 28 | Cancel API + terminal-state protection | api_backend | 0.25
Phase 6: Run pipeline + preview + download | 29 | CSV download API | api_backend | 0.25
Phase 6: Run pipeline + preview + download | 30 | Preview API | api_backend | 0.25
Phase 6: Run pipeline + preview + download | 31 | Pipeline/run property + integration tests | testing | 2 | Yes
Phase 7: Frontend (Angular Customer Portal extension) | 32 | Flow-canvas library spike | frontend | 2 | Yes
Phase 7: Frontend (Angular Customer Portal extension) | 33 | Shared client `Report_Design` model + graph mapping | frontend | 1
Phase 7: Frontend (Angular Customer Portal extension) | 34 | Screens | frontend | 2
Phase 8: Hardening, tests, deploy | 35 | Security test suite | testing | 2
Phase 8: Hardening, tests, deploy | 36 | Observability | integration | 0.5 | Yes
Phase 8: Hardening, tests, deploy | 37 | CI/CD pipeline for `BrytReportBuilder | integration | 0.5 | Yes
Phase 8: Hardening, tests, deploy | 38 | End-to-end walkthrough against a dev stage + sign-off | integration | 0.5